## Slide 1
Design Process Update
Ideation & initial sketching for whiteboard calendar template
Conducted preliminary user interviews about calendar needs, habits, preferences, workflows, etc.
Ideation & sketches for screen display based on initial user research
Team Name
Project Name
Current Milestone
Current Week
Minimum viable data capture
Week 6 and 7
Ambient Interfaces: The Social Family
\lambda
Activities Planned
Status Overview
Key Activities & Achievements
PROJECT STATUS REPORT
Conduct testing with whiteboard calendar designs to gauge user flows & resolve best options
Finalise screen display prototype sketches based on feedback from other sub-teams
Conduct additional user interviews about calendar needs, habits, etc. as well as location perceptions
Minimum viable data capture | 10/9/23 | - | -
Minimum viable backend ecosystem | 24/9/23 | 17/9/23 | -
Minimum viable physical prototype | 17/9/23 | 24/9/23 | -
Minimum viable software ecosystem | 8/10/23 | - | -
Minimum viable product ecosystem | 15/10/23 | - | -
Product, documentation & auxiliaries | 18/10/23 | - | -
Estimated Finish
Revised Finish
Actual Finish
Key Milestones
Development Process Update
Activities Planned
Key Activities & Achievements
Schedule
Scope
Quality
Team Dynamics
Risk # | Description | Action | Level
1 | Camera trigger pathway unclear | Alex & Ali investigate | 
2 | Data privacy & security of DB microservice | Lucas & David investigate | 
3 | Differing front end stack familiarities | Maya & Ali discuss & resolve | 
Key Risks and Issues
Implemented & tested basic version of database and microservice
Implemented core logic for input data capture processing in Python
Developed satisfactory physical prototype to begin planning for physical construction
Preliminary design of system component comms./architecture
Confirm incoming & outgoing JSON format and processing to be performed by database
Finalise planned approach for input data capture logic
Plan React web app structure
Finalise physical specs & source remaining equipment
Continue revising architecture